## Discovery Phase
Nursing Agency Software APP- Discovery Phase
Item No. | Functionality | Comments | Milestones | Days | Cost (RS)
Project Kick off - Upfront / Advance payment
1 | Requirement Analysis and Feasibility study To develop a mobile application - a complete nursing recruitment automation with android and ios app |  | ONE
1.1 | Project Planning and Management
2 | User Interface and Experience Analysis & Designing | UI & UX
2.1 2.2 | Page / custom images Color selection Theme selection Preparing mockups based on requirements a. Admin b. APP functional pages c. APP static pages Responsive UI design Page Designing based on the approved mockup | Daily interaction with the client for reviewing the designs done. After confirmation will close the design and move to the prototype Resource Allocation 2 Designers 1 Analyst
3 | Prototype Development | HTML
3.1 | Page Designing Html integration Converting UI into responsive HTML | 2 Html programmers
3.2 | Page navigation flow creation
4 | Phase ONE Testing - Design & Prototype
4.1 | Final testing of design phase Testing the UI & UX in the application both for Admin and End users | Corrections if needed (better to implement corrections before html of a page) Resource Allocation 1 resource (design/html) 1 Analyst
Estimation is based on the requirement doc and video provided. If any further functionalities are to be added in the above scenarios then man-days can increase accordingly Any change or add-ons in the above Design phase can increase the cost.
Total Days / Cost | Days may vary which depends on the client's response, more changes based on new requirements and also for any UI changes. Days exclude weekends, public holidays |  |  | 0 | Rs0
| Initial Deposit | 30% of total amount
Due on Receipt

## Implementation Phase
Nursing Agency Software - Development Phase
Item No. | Functionality | Comments | Milestones | Days | Cost (Rs:)
Functional criteria WEB Application
1 | APP Administrator Sign Up - Login, Forgot Password User management Change Admin user/password details. Control Static Pages in all other auxiliary pages, header, footer etc. Manage contents Manage images Manage Manage newsletter Manager The administration panel can be designed to provide 100% control over the APP functionality. A very easy-to-use admin panels/layout with proper terminology and images. |  | TWO
2
2 | Splash screen
Walkthrough [If needed]
Homepage
3 | Header
Logo
Header menu
| Activity logs Select Role Select Module From To Search | Activity logs for the searched is displayed in a table format with headings Date & Time Agency Name User Module Actions
| Push notifications No unseen notifications found View all notifications | View all notifications - can set the number of notifications to be shown in the page
| Settings |  | THREE
| Add/modify Job Roles | View job roles
| Add/modify Document Types Table will list:- Sl No Category - for eg Address proof Document type - for eg: Bank Statement Action buttons - Edit and Delete | View document types Pagination
| Change Invoice Due Date | Invoice due days
| Change Invoice creation period | Invoice creation period
| Candidate Deduction | Yes or No
| Manage Users Select the role and check the privilege for that particular role | Assign privileges
| Select Invoice Template Template will have:- Logo Company Name Address Title - Invoice Invoice to address Invoice number Date of invoice Invoice period Due date Service User Table with details:- Dates Candidates Quantity Rate Amount Terms and Conditions | Set template
| Add Terms & Conditions for Invoice Text editor Text box to type in the content Submit button | Set Terms and Conditions | FOUR
| VAT Registered | Yes or No
| Add Holidays The page will display the calendar where user can move to each month and mark the holidays for the calendar year. | Set holidays
| Email Integration | Integrate your email
My Profile
| Can edit the created profile and update the profile. | Agency code and name - no edit
Master
| Add Super Admin | To add the super admin details
| View all Super Admin | To view all super admin details
Add Client / Business Unit
| Add client details Add business unit details | Can view all the created client and business unit details
Add job roles
| Can add a job role name Actions buttons - Edit and Delete | Can view all the crated job roles
Add job
| Select Client Select Business Unit Job Title Action buttons - To add new job role, to view all job roles created | All client listed in dropdown All business unit listed in dropdown Select the designation
Add Client Rate
| Select Client Select Business Unit Select Job Week Days (enter amount for weekdays) Night Time (enter amount for nights) Friday Night (enter amount for Friday night) Saturday Day (enter amount for Saturday day) Saturday Night (enter amount for Saturday night) Sunday Day (enter amount for Sunday day) Sunday Night (enter amount for Sunday night) Public Holiday Day (enter amount for public holiday day) Public Holiday Night (enter amount for public holiday night) | View button to see all the created client rates (action buttons view, edit and delete) Copy from another client rate
Add Staff Rate
| Select Client Select Business Unit Select Job Select Employment Type Week Days: (enter amount for week days) Night Time (enter amount for nights) Friday Night (enter amount for Friday night) Saturday Day (enter amount for Saturday day) Saturday Night (enter amount for Saturday night) Sunday Day (enter amount for Sunday day) Sunday Night (enter amount for Sunday night) Public Holiday Day (enter amount for public holiday day) Public Holiday Night (enter amount for public holiday night) | View all staff rates
Add Vacancies
| Reference no Client (select from dropdown) Business Unit (select from dropdown) Job (select from dropdown) Location Detail Date Shift Type (select from dropdown) Break Time Space | View all vacancies
Add Document Type
| Category (select the category) Document Type (enter the document type) | View all document types
| Candidates |  | FIVE
Add Candidate
| First Name Middle Names Surname Gender Date of Birth Address Country Postcode Designation DBS/PVG Number DBS/PVG Issue Date Staff ID Payroll ID Email address PIN Number PIN Expiry Date Phone Country Code Phone Number Mobile Country Code Mobile Number Employment Type Status | Candidate Name & Address Details
| NI Number Passport Number Issuing Country Visa Type | Candidate NI & Passport Details
| Upload photo Select Document Type Date of issue Date of expiry Document (upload or delete the uploaded document) | Candidate Certificates & Photos
View all candidates Upload candidates from CSV (import excel sheet)
View candidate profile Edit Candidate Send login details
Add Candidate Availability View Candidate Availability
Deactivated candidates
Timesheets
| Select Client Select Business Unit Select Job Total Cost Total Hours | All timesheets
Selected details get listed in the below table Can search the details
| Bookings | All Bookings | SIX
Select Client Select Business Unit Select Job From To
| On click Search will list the details of bookings selected | View deleted bookings Download the page as CSV
| Historical (Timesheet) | All Historical Time sheets
Select Client Select Business Unit Select Job Week Ending Total Cost Total Hours
Based on the selected data the details get listed below. Can search from the listed data
Can select all the listed details and can either approve or delete
| Invoice | All Client Invoices
Create Invoices
Select Client Select Business Unit Invoice No
Selected invoices is listed below
| Candidate Invoices | All Candidate Invoices
All candidate invoices are listed
Vacancies
View all vacancies
Add a vacancy
Send notifications
Push notifications Send Push Notifications Enter the message Search for the first name Send the notification
Text notifications Send Text Message Notifications Enter text message Select for first name Send the notification
Email Notifications Send Email notification Select To Single recipient or Multiple recipient Enter the email address Enter the subject Type the message (text editor) Attach file (upload) Send email
| Reports |  | SEVEN
Time sheet report
Time sheet Summary Week Start Date Week End Date Select Client Select Business Unit Get report based on the selection
Live Time sheets
Select Client Select Business Unit Get report based on the selection
Candidate wise report
Week Start Date Week End Date Employment Type Select Client Select Business Unit Candidate Get report based on the selection
Business Unit wise
Week Start Date Week End Date Select Client Select Business Unit Get report based on the selection
3.2 | Menu header
Login page
User name
Password
Sign up
Agency name
Name of the Authorized person
Address
Post Code
Phone number
| Agency Logo | Select Photo
Email address
| VAT Registered ? | Yes or No If yes provide VAT registration number
Password
Confirm password
| Agree Terms and Conditions | Checkbox
Sign up button
Dashboard
Timesheets Staff Cost Total amount Total hours
Candidate documents Due for Renewal Expired
Vacancies New applications Total positions available
Schedules
Invoices Unpaid Last 4 weeks
Profit and Loss Last 4 weeks
Logout
5 | Footer
Will have links to the different pages in the application.
FAQ Terms and Conditions Support
10 | Responsive Designs Mobile optimization
Responsive Designs will be made to fit the APP on any screen size resolutions of any mobile devices, Tablet etc. with perfect widths, pixels and high flexibility. Cross browser Compatibility (Google chrome, Mozilla Firefox etc.)
11 | Final Implementing, Testing and Debugging
Testing the UI and complete features in the application both for Admin and End users (UAT)
Estimation is based on the requirement and video shared. If any further functionalities are to be added in the above scenarios then man-days can increase accordingly Any change or add-ons in the above Development phase can increase the days and cost.
Total Days / Cost | Days may vary which depends on the client's response, more changes based on new requirements and also for any UI changes. Days exclude weekends, public holidays |  |  | 0 | Rs.0
Initial Deposit
Due on Receipt