## Discovery Phase
Pharma Educare Society Discovery Phase
Copyright© 2019 Srishti Innovative Information in this document is subject to change without notice and do not represent a commitment on the part of Srishti Innovative. No part of this document may be reproduced or retransmitted in any form or by any means, whether electronically or mechanically, including, but not limited to the way of Photo Copying, Recording or through any other means of information recording and retrieval system without the express written consent of Srishti Innovative. The information in the document is believed to be precise in all respects to the best of our knowledge at the time of release and is subject to change without prior notice. Srishti Innovative is not legally liable for any errors or opinions that appear in this document. All trademarks and logos used in this document are the property of the respective owner.
Item No. | Functionality | Comments | Milestones | Days | Cost (USD)
Project Kick off - Upfront / Advance payment
1 | Requirement Analysis and Feasibility study To develop a software platform for educational purpose. |  | ONE
1.1 | Project Planning and Management
2 | User Interface and Experience Analysis & Designing | UI & UX
2.1 2.2 | Logo Creation Page / custom images Color selection Theme selection Preparing mockups based on requirements a. Admin b. Website functional pages c. Website static pages Responsive UI design Page Designing based on the approved mockup | Daily interaction with the client for reviewing the designs done. After confirmation will close the design and move to the prototype Resource Allocation 2 Designers 1 Analyst
3 | Prototype Development | HTML | TWO
3.1 | Page Designing Html integration Converting UI into responsive HTML | 2 Html programmers
3.2 | Page navigation flow creation
4 | Phase ONE Testing - Design & Prototype |  | THREE
4.1 | Final testing of design phase Testing the UI & UX in the application both for Admin and End users | Corrections if needed (better to implement corrections before html of a page) Resource Allocation 1 resource (design/html) 1 Analyst
Estimation is based on Pharma Educare Society. If any further functionalities are to be added in the above scenarios then man-days can increase accordingly Any change or add-ons in the above Design phase can increase the cost.
Total Days / Cost | Days may vary which depends on the client's response, more changes based on new requirements and also for any UI changes. Days exclude weekends, public holidays |  |  | 0 | $0
| Initial Deposit | 30% of total amount
Due on Receipt

## Implementation Phase
Pharma Educare Society WEB Application - Development Phase
Copyright© 2019 Srishti Innovative Information in this document is subject to change without notice and do not represent a commitment on the part of Srishti Innovative. No part of this document may be reproduced or retransmitted in any form or by any means, whether electronically or mechanically, including, but not limited to the way of Photo Copying, Recording or through any other means of information recording and retrieval system without the express written consent of Srishti Innovative. The information in the document is believed to be precise in all respects to the best of our knowledge at the time of release and is subject to change without prior notice. Srishti Innovative is not legally liable for any errors or opinions that appear in this document. All trademarks and logos used in this document are the property of the respective owner.
Item No. | Functionality | Comments | Milestones | Days | Cost (USD)
Functional criteria
1 | Admin Sign Up - Login, Forgot Password User Management Change Admin user/Password details. Control Static Pages in all other auxiliary pages, header, footer etc. Manage Users Manage Contents Manage Images Manage Payment Manage Package Manage Subject The administration panel can be designed to provide 100% control over the APP functionality. A very easy-to-use admin panels/layout with proper terminology and images. |  | ONE
2
2 | User |  | TWO
2.1 | User Dashboard
2.2 | User can select paid packages for online test
2.3 | Leader Board-
2.4 | My Exams
2.5 | My Results
2.6 | My Payment
2.7 | Take an exam
2.8 | They can User test
3 | General User |  | THREE
3.1 | Generate results
3.2 | Payment
3.3 | Register/Login
4 | Responsive Designs Mobile optimization |  | FOUR
Test to ensure site works in various browsers and on laptop, tablet and mobiles devices Responsive Designs will be made to fit the website on any screen size resolutions of any devices like Mobile, Laptop, PC etc. with perfect widths, pixels and high flexibility. Cross browser Compatibility (Google chrome, Mozilla Firefox etc.)
5 | Final Implementing, Testing and Debugging
Testing the UI and complete features in the application both for Admin and End users (UAT)
Estimation is based on Pharma Educare Society. If any further functionalities are to be added in the above scenarios then man-days can increase accordingly Any change or add-ons in the above Development phase can increase the days and cost.
Total Days / Cost | Days may vary which depends on the client's response, more changes based on new requirements and also for any UI changes. Days exclude weekends, public holidays |  |  | 0 | $0
Initial Deposit
Due on Receipt